## Index
VNC — SCA Service Line Implementation & Milestone Plans
One tab per service line: an implementation task plan (Task ID / Phase / Workstream / Task / VNC Owner / Predecessor) and a milestone tracker (Milestone ID / Target Timing / Owner / Status / Evidence-Acceptance).
Sheet | Service | Engagement Type | Typical Duration
1 Cin7 Core Setup | Cin7 Core Setup & Integration | One-time project | 2-8 weeks (Starter/Growth/Advanced)
2 Rescue & Clean-Up | Rescue & Clean-Up | One-time project | 2-8 weeks
3 System Assessment | System Assessment & Process Improvement | One-time project | 1-2 weeks
4 Inventory Accounting | Inventory Accounting | Recurring (onboarding + monthly) | Ongoing, monthly cadence
5 E-Commerce Accounting | E-Commerce Accounting | Recurring (onboarding + monthly) | Ongoing, monthly cadence
6 Reporting & Analysis | Reporting & Analysis | Recurring (onboarding + tiered cadence) | Ongoing, monthly/quarterly per tier
Design notes: (1) Timing shown as relative (Week/Day/Month N), not fixed calendar dates, since this is a reusable template rather than one dated client engagement — insert real dates when scoping an actual client. (2) 'VNC Owner' uses the real internal role titles from VNC's Team Structure document (Practice Lead, Onboarding Consultant, Technical Consultant, Delivery Lead, Consultant, Analyst); client-side roles (Client PM, Controller, Operations Lead, Project Sponsor) are kept generic since they vary by client org.

## SCA Template
SCA / EFA / ANZA | Client Number - Client Name | Service List | [7 empty] | ( Internal Due date ) |  | ( Map to CHS Section 3 dropdown ) |  |  | For any ad hoc tasks created | For recurring tasks | only for compliane tasks | People | Link of sharepoint / zoho learn process doc |  | task names that must finish first, comma-separated | Task name this task blocks
Space | Folder | List | Tasks | Sub Tasks if any | Status | Role | Assignee | Priority | Start Date | Due Date | Time Estimate | Key Priority | Project Milestones | Billing Type | Source | Month | Compliance Due date | Back up person | Sharepoint Link | Tags | Depends on | Blocking
SCA Team | C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Kick-off, Introduction, System access & project charter agreed |  | Done | Manager | Aamir Shaikh | High | 2026-07-06 | 2026-07-06 | 1h | Sec 3 - Implementation | 1 Kickoff |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Confirm in-scope entities (SKUs, locations, channels, suppliers, customers) |  | Done | Manager | Aamir Shaikh | Normal | 2026-07-06 | 2026-07-07 | 2h | Sec 3 - Implementation | 1 Kickoff |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Costing method, BOM configuration, Pricing Tiers and Supplier Rules setup (All) |  | In Progress | Assistant Team Lead | Ganesh Rathore | Normal | 2026-07-07 | 2015-07-01 | 1h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | COA GL mapping, Tracking category design & Setup |  | In Progress | Assistant Team Lead | Ganesh Rathore | Normal | 2026-07-07 | 2015-07-01 | 2h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | General Setup and Reference books Configuration |  | In Progress | Assistant Team Lead | Ganesh Rathore | Normal | 2026-07-07 | 2015-07-01 | 2h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Product Master (BOM) Cleanup and Import |  | In Progress | Inventory Analyst | Maaz Sodagar | Normal | 2026-07-07 | 2015-07-01 | 5h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Products Assembly Configuration |  | In Progress | Assistant Team Lead | Ganesh Rathore | Normal | 2026-07-07 | 2015-07-01 | 2h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Suppliers Master Cleanup and Import |  | In Progress | Inventory Analyst | Maaz Sodagar | Normal | 2026-07-07 | 2015-07-01 | 2h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Customer Master Cleanup and Import |  | In Progress | Inventory Analyst | Maaz Sodagar | Normal | 2026-07-07 | 2015-07-01 | 2h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Additional Attributes setup and Import |  | In Progress | Inventory Analyst | Maaz Sodagar | Normal | 2026-07-07 | 2015-07-01 | 2h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Reorder function Setup ( ROL, Lead time, Min - Max) |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-07-07 | 2015-07-01 | 2h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Configure opening balances (Stock, TB, AP, AR) |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 5h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Configure opening balances (Open & In transit PO, SO, Production Runs / Assemblies) |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 5h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Configure User Roles & Controls |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Setup Document Templates (Sales, Purchases, Inventory) |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 5h | Sec 3 - Implementation | 1 Master Data |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Setup Sales and Purchase List view under each Module |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 1:30h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Setup Workflow Steps Purchase Module ( Procure to pay) |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 1:30h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Setup Workflow Steps Sale Module ( Order to Cash) |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 1:30h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Configure Fulfilment setup > Pick Pack ship |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 1:30h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Configure Invoicing, Service Purchase and GRN setup |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 1:30h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Set up landed costs & supplier expense allocation |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 1:30h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Integration Setup Accounting System | Define the data Integration flow and sync rules |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Integration Setup Accounting System | Configure Integration Page, Syncing rules and Sync workflow |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 2 Config |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Integration Setup Accounting System | Opening Balances / Conversion balnaces Reconciliation and Cut off |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 5 Integration Stabilisation |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Integration Setup Accounting System | Author UAT scripts & Scenarios (O2C, P2P, IM, F&A) |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 5h | Sec 3 - Implementation | 5 Integration Stabilisation |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Integration Setup Accounting System | Workflow Documentation & Parallel run commences |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2015-07-01 | 2031-07-01 | 10h | Sec 3 - Implementation | 5 Integration Stabilisation |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | UAT execution across cycles - Purchase Module |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 3 Testing |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | UAT execution across cycles - Sales Module |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 3 Testing |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | UAT execution across cycles - Inventory Module |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 3 Testing |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | UAT execution across cycles - Integrated Accounting system Module |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 2h | Sec 3 - Implementation | 3 Testing |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Resolve data discrepancies & Client feedback cases |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 10h | Sec 3 - Implementation | 3 Testing |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | UAT sign-off |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2015-07-01 | 2031-07-01 | 1h | Sec 3 - Implementation | 4 Go-Live |  |  | 2026-07-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Training materials & quick-reference cards |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-08-01 | 2026-08-14 | 2h | Sec 3 - Implementation | 4 Go-Live |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | User training sessions |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-08-01 | 2026-08-14 | 4h | Sec 3 - Implementation | 4 Go-Live |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Cutover / go-live |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-08-01 | 2026-08-14 | 1h | Sec 3 - Implementation | 4 Go-Live |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Weekly post-go-live health checks |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-14 | 5h | Sec 3 - Implementation | 4 Go-Live |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | UAT sign-off |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-08-01 | 2026-08-14 | 1h | Sec 3 - Implementation | 6 Handover |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Configure month-of-stock availability reporting |  | Not Started | Manager | Aamir Shaikh | Normal | 2026-08-01 | 2026-08-14 | 5h | Sec 3 - Implementation | 2 Recurring Monthly Cycle |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | First month-end close with client |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-08-01 | 2026-08-14 | 5h | Sec 3 - Implementation | 2 Recurring Monthly Cycle |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Deliver monthly controller reports (margin, BOM cost, COGS, trends) |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-08-01 | 2026-08-14 | 5h | Sec 3 - Implementation | 2 Recurring Monthly Cycle |  |  | 2026-08-01
| C-000499 - Industrial Brushware Pty Ltd | Cin7 Core Setup & Integration | Hypercare complete & closeout; handoff to ongoing support |  | Not Started | Assistant Team Lead | Ganesh Rathore | Normal | 2026-08-01 | 2026-08-14 |  | Sec 3 - Implementation | 6 Handover |  |  | 2026-08-01
| C-000025 - Cambie Distribution | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Order-to-cash processing (orders, invoices, fulfilment) |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-01 | 00:30h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-daily
| C-000025 - Cambie Distribution | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Procure-to-pay processing (purchases, receipts, bills) |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-01 | 00:30h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-daily
| C-000025 - Cambie Distribution | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Landed cost & COGS accuracy check |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-02 | 1h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-weekly
| C-000025 - Cambie Distribution | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Stock adjustment monitoring |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-02 | 2h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-weekly
| C-000025 - Cambie Distribution | Cin7 Core System Assessment | Sales channel connections review |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-02 | 2h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-weekly
| C-000025 - Cambie Distribution | Cin7 Core System Assessment | Stock movement & COGS accuracy review |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-02 | 1h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-weekly
| C-000025 - Cambie Distribution | Cin7 Core System Assessment | Workflow gaps & manual workaround review |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-02 | 1h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-weekly
| C-000025 - Cambie Distribution | Cin7 Core System Assessment | Reporting reliability & data trust review |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-01 | 2026-08-02 | 2h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-weekly
| C-000025 - Cambie Distribution | Cin7 Core System Assessment | Inventory accuracy & valuation review |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-26 | 2026-09-08 | 2h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-monthly
| C-000025 - Cambie Distribution | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Monthly inventory & operational review pack |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal | 2026-08-26 | 2026-09-08 | 5h | Sec 3 - Month End | 2 Recurring Monthly Cycle |  |  | 2026-08-01 |  |  |  | recurring-monthly
|  |  | email mailbox missing in Service task list |  | Not Started | Inventory Analyst | Maaz Sodagar | Normal

## SCA Dropdown Options
Business Unit - SCA | Client Number - Client Name | Service List | [7 empty] | ( Internal Due date ) |  | ( Map to CHS Section 3 dropdown ) |  |  | For any ad hoc tasks created | For recurring tasks | only for compliane tasks | People | Link of sharepoint / zoho learn process doc |  | task names that must finish first, comma-separated | Task name this task blocks
Space | Folder | List | Tasks | Sub Tasks if any | Status | Role | Assignee | Priority | Start Date | Due Date | Time Estimate | Key Priority | Project Milestones | Billing Type | Source | Month | Compliance Due date | Back up person | Sharepoint Link | Tags | Depends on | Blocking
SCA | C-000025 - Cambie Distribution | Cin7 Core Setup & Integration | NA | NA | Not Started | Inventory Analyst | Aamir Shaikh | Urgent | dd/mm/yyyy | dd/mm/yyyy | 00:30 Hours | Sec 3 - Financial Reviews | 1 Master Data | In Scope | Emails | 2026-01-01 |  |  |  | recurring-daily
| C-000092 - Medigroup ( Australia ) Pty Ltd | Integration Setup Accounting System |  |  | In Progress | Assistant Team Lead | Ganesh Rathore | High |  |  | 01:00 Hours | Sec 3 - Month End | 2 Config | Out of Scope | Slack | 2026-02-01 |  |  |  | recurring-weekly
| C-000104 - Nsaaba LLC | Integration Setup Sales Channel |  |  | Under Review | Manager | Aliakbar Vohra | Normal |  |  |  | Sec 3 - Documentation | 3 Testing | Internal | Whatsapp | 2026-03-01 |  |  |  | recurring-fortnightly
| C-000152 - Tillfield Ltd | Integration Setup Shipping / 3PL Channel |  |  | Done | Associate | Maaz Sodagar | Low |  |  |  | Sec 3 - Optimisation / Automation | 4 Go-Live |  |  | 2026-04-01 |  |  |  | recurring-monthly
| C-000351 - Outnabout | Cin7 Core Rescue & Clean-Up |  |  | Waiting for info(Client) |  | Hitanshi Vaidya |  |  |  |  | Sec 3 - Accuracy & Bookkeeping | 1 Diagnosis |  |  | 2026-05-01 |  |  |  | recurring-quarterly
| C-000438 - Squirro AG | Cin7 Core System Assessment |  |  | On hold | [6 empty] | Sec 3 - Oldest Open task | 2 Reconciliation |  |  | 2026-06-01 |  |  |  | recurring-yearly
| C-000476 - Chef Works Pte Ltd | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | [9 empty] | Sec 3 - Training / Handover | 3 Error Correction |  |  | 2026-07-01
| C-000477 - Half Past Seven Home | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | [9 empty] | Sec 3 - Planned Vs Actual time | 4 Standardisation |  |  | 2026-08-01
| C-000483 - OLA MATE | Cin7 Core Monthly Constroller Support - Reporting & Analysis | [9 empty] | Sec 3 - Revenue growth & Scope expansion | 5 Integration Stabilisation |  |  | 2026-09-01
| C-000484 - Audien LLC (Audien Hearing) | [10 empty] | Sec 3 - Hours spent | 6 Handover |  |  | 2026-10-01
| C-000485 - Austin Historical LLC | [10 empty] | Sec 3 - Integration | 1 Kickoff |  |  | 2026-11-01
| C-000489 - Ethos Car Care | [10 empty] | Sec 3 - Implementation | 2 Access & Data |  |  | 2026-12-01
| C-000490 - Lumia Health | [10 empty] | Sec 3 - Go Live | 3 System Health Check
| C-000493 - Pokoloko | [10 empty] | Sec 1 - Revenue Growth (YoY %) | 4 Gap Analysis
| C-000495 - Agilitas Australia | [10 empty] | Sec 1 - Profit % ( Current YTD) | 5 Workflow Review
| C-000496 - Werko Australia | [10 empty] | Sec 1 - AR > 90 days ( % of Total AR) | 6 Roadmap & Handover
| C-000497 - Greenwood Leather | [10 empty] | Sec 1 - AP > 90% days ( % of Total AP) | 1 Onboarding
| C-000499 - Industrial Brushware Pty Ltd | [10 empty] | Sec 2 - Client Responsiveness | 2 Recurring Monthly Cycle
[12 empty] | Sec 2 - Critical Escalations by client ( last 3 months ) | 2 Recurring Cycle
Sec 2 - Scope of work
Sec 2 - Billing / Revenue Amount
Sec 2 - Currency
Sec 2 - Invoice Overdue days ( Beyound Due Dates )

## Master Mapping
VNC SCA — Master Mapping: Service → Workstream → Milestone → Task → Role → Standard Duration
Standard Duration figures are planning-estimate defaults, not measured data — calibrate against real TUR (time utilisation report) actuals once available across a few live engagements, and update this sheet rather than treating these as fixed.
SCA Team | Client | List | Custom Field | Custom Field | Task | Assignee | Time Estimate
Space | Folder | Service | Workstream | Milestone | Task | Role | Standard Duration
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Kick-off, Introduction, System access & project charter agreed | Consultant PM | 2 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Confirm in-scope entities (SKUs, locations, channels, suppliers, customers) | Consultant PM | 3 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Costing method, BOM configuration, Pricing Tiers and Supplier Rules setup (All) | Analyst / ATL | 1 hr
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | General Setup and Reference books Configuration | Analyst / ATL | 6 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | COA GL mapping, Tracking category design & Setup | Analyst / ATL | 6 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Product Master (BOM) Cleanup and Import | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Products Assembly Configuration | Analyst / ATL | 4 hrs (client)
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Suppliers Master Cleanup and Import | Analyst / ATL | 4 hrs (client)
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Customer Master Cleanup and Import | Analyst / ATL | 8 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Additional Attributes setup and Import | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Reorder function Setup ( ROL, Lead time, Min - Max) | Analyst / ATL | 6 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Configure opening balances (Stock, TB, AP, AR) | Analyst / ATL | 6 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Configure opening balances (Open & In transit PO, SO, Production Runs / Assemblies) | Analyst / ATL | 3 hrs
|  | Cin7 Core Setup & Integration | Implementation | 1 Master Data | Configure User Roles & Controls | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Implementation | 2 Config | Setup Document Templates (Sales, Purchases, Inventory) | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Implementation | 2 Config | Setup Sales and Purchase List view under each Module | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Implementation | 2 Config | Setup Workflow Steps Purchase Module ( Procure to pay) | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Implementation | 2 Config | Setup Workflow Steps Sale Module ( Order to Cash) | Analyst / ATL | 3 hrs
|  | Cin7 Core Setup & Integration | Implementation | 2 Config | Configure Fulfilment setup > Pick Pack ship | Analyst / ATL | 6 hrs
|  | Cin7 Core Setup & Integration | Implementation | 2 Config | Configure Invoicing, Service Purchase and GRN setup | Analyst / ATL | 2 hrs
|  | Cin7 Core Setup & Integration | Implementation | 2 Config | Set up landed costs & supplier expense allocation | Analyst / ATL | 4 hrs
|  | Integration Setup Accounting System | Integration | 2 Config | Define the data Integration flow and sync rules | Consultant PM | 6 hrs
|  | Integration Setup Accounting System | Integration | 2 Config | Configure Integration Page, Syncing rules and Sync workflow | Analyst / ATL | 3 hrs
|  | Integration Setup Accounting System | Integration | 3 Testing | Opening Balances / Conversion balnaces Reconciliation and Cut off | Analyst / ATL | 4 hrs
|  | Integration Setup Accounting System | Integration | 3 Testing | Author UAT scripts & Scenarios (O2C, P2P, IM, F&A) | Analyst / ATL | 4 hrs
|  | Integration Setup Accounting System | Integration | 3 Testing | Workflow Documentation & Parallel run commences | Analyst / ATL | Ongoing (1 cycle, client)
|  | Integration Setup Sales Channel | Integration | 2 Config | Define the data Integration flow and sync rules | Consultant PM | 6 hrs
|  | Integration Setup Sales Channel | Integration | 2 Config | Configure Integration Page, Syncing rules and Sync workflow | Analyst / ATL | 3 hrs
|  | Integration Setup Sales Channel | Integration | 3 Testing | Author UAT scripts & Scenarios (O2C, P2P, IM, F&A) | Analyst / ATL | 4 hrs
|  | Integration Setup Sales Channel | Integration | 3 Testing | Workflow Documentation & Parallel run commences | Analyst / ATL | Ongoing (1 cycle, client)
|  | Integration Setup Shipping / 3PL Channel | Integration | 2 Config | Define the data Integration flow and sync rules | Consultant PM | 6 hrs
|  | Integration Setup Shipping / 3PL Channel | Integration | 2 Config | Configure Integration Page, Syncing rules and Sync workflow | Analyst / ATL | 3 hrs
|  | Integration Setup Shipping / 3PL Channel | Integration | 3 Testing | Author UAT scripts & Scenarios (O2C, P2P, IM, F&A) | Analyst / ATL | 4 hrs
|  | Integration Setup Shipping / 3PL Channel | Integration | 3 Testing | Workflow Documentation & Parallel run commences | Analyst / ATL | Ongoing (1 cycle, client)
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | UAT execution across cycles - Purchase Module | Analyst / ATL | 2 days (client)
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | UAT execution across cycles - Sales Module | Analyst / ATL | 2 days (client)
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | UAT execution across cycles - Inventory Module | Analyst / ATL
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | UAT execution across cycles - Integrated Accounting system Module | Analyst / ATL
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | UAT execution across cycles - Integrated OMS Module | Analyst / ATL | 2 hrs (client)
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | UAT execution across cycles - Integrated WMS Module | Analyst / ATL | 2 hrs (client)
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | Resolve data discrepancies & Client feedback cases | Analyst / ATL | 4 hrs (variable)
|  | Cin7 Core Setup & Integration | Go Live | 3 Testing | UAT sign-off | Consultant PM | 1 hr (client)
|  | Cin7 Core Setup & Integration | Go Live | 4 Go-Live | Training materials & quick-reference cards | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Go Live | 4 Go-Live | User training sessions | Analyst / ATL | 4 hrs
|  | Cin7 Core Setup & Integration | Go Live | 4 Go-Live | Cutover / go-live | Consultant PM | 4 hrs
|  | Cin7 Core Setup & Integration | Go Live | 4 Go-Live | Weekly post-go-live health checks | Analyst / ATL | 2 hrs/week
|  | Cin7 Core Rescue & Clean-Up | PM | 1 Diagnosis | Kick-off call & scope confirmation | Consultant PM | 2 hrs
|  | Cin7 Core Rescue & Clean-Up | Access | 1 Diagnosis | Collect system access (Cin7, Xero/QBO, Shopify/Amazon, A2X) | Consultant PM | 2 hrs
|  | Cin7 Core Rescue & Clean-Up | Audit | 1 Diagnosis | Inventory accuracy & valuation audit | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Audit | 1 Diagnosis | Accounting integration health audit (sync, mapping, postings) | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Audit | 1 Diagnosis | Sales channel connections audit (payout recon health) | Analyst / ATL | 3 hrs
|  | Cin7 Core Rescue & Clean-Up | Audit | 1 Diagnosis | Workflow gaps & manual workaround audit | Consultant PM | 3 hrs
|  | Cin7 Core Rescue & Clean-Up | Audit | 1 Diagnosis | Stock movement & COGS accuracy audit | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Audit | 1 Diagnosis | Reporting reliability & data trust audit | Consultant PM | 3 hrs
|  | Cin7 Core Rescue & Clean-Up | Findings | 1 Diagnosis | Findings documented & priority-ranked (Red/Amber/Green) | Consultant PM | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Recon | 2 Reconciliation | Reconcile stock quantities across locations | Analyst | 6 hrs
|  | Cin7 Core Rescue & Clean-Up | Recon | 2 Reconciliation | Reconcile valuations & landed costs | Analyst / ATL | 6 hrs
|  | Cin7 Core Rescue & Clean-Up | Recon | 2 Reconciliation | Reconcile warehouse balances | Analyst | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Recon | 2 Reconciliation | Bank/control account reconciliation baseline | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Fix | 3 Error Correction | Fix SKU mapping issues | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Fix | 3 Error Correction | Remove duplicate records | Analyst | 3 hrs
|  | Cin7 Core Rescue & Clean-Up | Fix | 3 Error Correction | Correct incorrect postings | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Fix | 3 Error Correction | Repair broken integrations | Analyst / ATL | 6 hrs
|  | Cin7 Core Rescue & Clean-Up | Standardise | 4 Standardisation | Align SKU / category / location structure | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Standardise | 4 Standardisation | Standardise workflows across systems | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Document | 4 Standardisation | Document standardised SOPs | Consultant PM | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Stabilise | 5 Integration Stabilisation | Stabilise accounting system integration | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Stabilise | 5 Integration Stabilisation | Stabilise e-commerce channel & A2X integration | Analyst / ATL | 4 hrs
|  | Cin7 Core Rescue & Clean-Up | Stabilise | 5 Integration Stabilisation | Stabilise shipping tool integrations | Analyst / ATL | 3 hrs
|  | Cin7 Core Rescue & Clean-Up | Validate | 5 Integration Stabilisation | Validate stability across 2 consecutive sync cycles | Analyst / ATL | Ongoing (2 cycles)
|  | Cin7 Core Rescue & Clean-Up | Sign-off | 6 Handover | Historical data clean-up sign-off | Consultant PM | 1 hr (client)
|  | Cin7 Core Rescue & Clean-Up | Handover | 6 Handover | Prepare handover pack (findings, fixes, SOPs) | Consultant PM | 3 hrs
|  | Cin7 Core Rescue & Clean-Up | Handover | 6 Handover | Handover call to recurring delivery team | Analyst / ATL | 2 hrs
|  | Cin7 Core Rescue & Clean-Up | Transition | 6 Handover | Transition to Monthly Support confirmed | Consultant PM | 1 hr
|  | Cin7 Core System Assessment | PM | 1 Kickoff | Kick-off call (45-60 min): business model, warehouses/3PL, channels, pain points | Consultant PM | 1 hr
|  | Cin7 Core System Assessment | Scope | 1 Kickoff | Confirm systems in use (Cin7, Xero/QBO/MYOB, Shopify/Amazon, A2X, shipping) | Consultant PM | 1 hr
|  | Cin7 Core System Assessment | Scope | 1 Kickoff | Confirm assessment boundaries & expected deliverables | Consultant PM | 1 hr
|  | Cin7 Core System Assessment | Collection | 2 Access & Data | Collect read-only system access | Consultant PM | 2 hrs
|  | Cin7 Core System Assessment | Collection | 2 Access & Data | Request key reports (valuation, stock on hand, open SO/PO, payouts, TB) | Consultant PM | 1 hr
|  | Cin7 Core System Assessment | Tracking | 2 Access & Data | Maintain missing-items list | Consultant PM | 1 hr
|  | Cin7 Core System Assessment | Audit | 3 System Health Check | Inventory accuracy & valuation review | Analyst / ATL | 3 hrs
|  | Cin7 Core System Assessment | Audit | 3 System Health Check | Accounting integration health review | Analyst / ATL | 3 hrs
|  | Cin7 Core System Assessment | Audit | 3 System Health Check | Sales channel connections review | Analyst / ATL | 2 hrs
|  | Cin7 Core System Assessment | Audit | 3 System Health Check | Stock movement & COGS accuracy review | Analyst / ATL | 3 hrs
|  | Cin7 Core System Assessment | Audit | 3 System Health Check | Workflow gaps & manual workaround review | Analyst / ATL | 2 hrs
|  | Cin7 Core System Assessment | Audit | 3 System Health Check | Reporting reliability & data trust review | Analyst / ATL | 2 hrs
|  | Cin7 Core System Assessment | Analysis | 4 Gap Analysis | Process gap analysis | Analyst / ATL | 3 hrs
|  | Cin7 Core System Assessment | Analysis | 4 Gap Analysis | Data gap analysis (mappings, duplicates, categorisation) | Analyst / ATL | 3 hrs
|  | Cin7 Core System Assessment | Analysis | 4 Gap Analysis | Control gap analysis | Analyst / ATL | 2 hrs
|  | Cin7 Core System Assessment | Testing | 4 Gap Analysis | Practical data-quality tests (stock vs valuation trend, top-SKU cost checks) | Analyst | 3 hrs
|  | Cin7 Core System Assessment | Mapping | 5 Workflow Review | Map procure-to-pay end-to-end | Analyst / ATL | 2 hrs
|  | Cin7 Core System Assessment | Mapping | 5 Workflow Review | Map order-to-cash end-to-end | Analyst / ATL | 2 hrs
|  | Cin7 Core System Assessment | Mapping | 5 Workflow Review | Map inventory movements & identify break points | Analyst / ATL | 2 hrs
|  | Cin7 Core System Assessment | Roadmap | 6 Roadmap & Handover | Build prioritised roadmap (P1/P2/P3, effort bands, dependencies) | Consultant PM | 4 hrs
|  | Cin7 Core System Assessment | Report | 6 Roadmap & Handover | Prepare written assessment (plain language, no jargon) | Consultant PM | 4 hrs
|  | Cin7 Core System Assessment | Handover | 6 Roadmap & Handover | Handover call (45-60 min) | Consultant PM | 1 hr
|  | Cin7 Core System Assessment | Recommendation | 6 Roadmap & Handover | Recommend next path: A) Clean Implementation or B) Rescue + Implementation | Consultant PM | 1 hr
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Scope | 1 Onboarding | Confirm signed scope & planned monthly hours | Analyst / ATL | 1 hr
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Validation | 1 Onboarding | Validate SOP baseline (from Setup/Assessment/Rescue handover) | Analyst / ATL | 2 hrs
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Rhythm | 1 Onboarding | Define recurring rhythm (weekly + monthly checks) | Analyst / ATL | 2 hrs
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Staffing | 1 Onboarding | Assign Consultant/Analyst to account | Analyst / ATL | 1 hr
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Trial | 1 Onboarding | First cycle trial run & internal review | Analyst / ATL | 4 hrs
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | P2P | 2 Recurring Monthly Cycle | Procure-to-pay processing (purchases, receipts, bills) | Analyst | 4 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | O2C | 2 Recurring Monthly Cycle | Order-to-cash processing (orders, invoices, fulfilment) | Analyst | 4 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Integration | 2 Recurring Monthly Cycle | Cin7 ↔ Accounting integration check | Analyst / ATL | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Recon | 2 Recurring Monthly Cycle | Stock reconciliation (Cin7 vs accounting), monthly | Analyst / ATL | 3 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Costing | 2 Recurring Monthly Cycle | Landed cost & COGS accuracy check | Analyst / ATL | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Reporting | 2 Recurring Monthly Cycle | SKU-level profitability prep | Analyst / ATL | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Controls | 2 Recurring Monthly Cycle | Inventory controls & variance review | Analyst | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Controls | 2 Recurring Monthly Cycle | Stock adjustment monitoring | Analyst | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Operational Control and Inventory Accounting | Review | 2 Recurring Monthly Cycle | Monthly inventory & operational review pack | Analyst / ATL | 3 hrs/month
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Connect | 1 Onboarding | Connect sales channels (Shopify/Amazon/WooCommerce/etc.) | Analyst / ATL | 3 hrs
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Configure | 1 Onboarding | Configure A2X / Dext Commerce / Cin7 | Analyst / ATL | 3 hrs
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Validate | 1 Onboarding | Validate fee/refund/chargeback logic | Analyst / ATL | 3 hrs
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Rhythm | 1 Onboarding | Define payout reconciliation rhythm | Consultant PM | 2 hrs
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Trial | 1 Onboarding | First payout reconciliation trial run | Analyst / ATL | 4 hrs
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Revenue | 2 Recurring Monthly Cycle | Multi-channel revenue recognition | Analyst | 3 hrs/month
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Recon | 2 Recurring Monthly Cycle | Payout reconciliation (Shopify/Amazon/gateways) | Analyst / ATL | 4 hrs/month
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Match | 2 Recurring Monthly Cycle | Three-way match (channel → Cin7 → accounting) | Analyst / ATL | 3 hrs/month
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Costing | 2 Recurring Monthly Cycle | Stock, COGS & margin alignment | Analyst / ATL | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Fees | 2 Recurring Monthly Cycle | Fee & refund management | Analyst | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Reporting | 2 Recurring Monthly Cycle | Omni-channel reporting | Consultant PM | 3 hrs/month
|  | Cin7 Core Monthly Constroller Support - Ecommerce Accounting | Health | 2 Recurring Monthly Cycle | Automation/integration health check (as needed) | Analyst / ATL | 1 hr/month (as needed)
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Scope | 1 Onboarding | Confirm reporting tier (Visibility Essentials / Operational Insight / Decision Intelligence) | Consultant PM | 1 hr
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Scope | 1 Onboarding | Define report set & delivery frequency | Consultant PM | 2 hrs
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Build | 1 Onboarding | Build initial dashboard/report templates | Analyst / ATL | 6 hrs
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Rhythm | 1 Onboarding | Agree review call cadence | Consultant PM | 1 hr
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Inventory | 2 Recurring Cycle | Inventory & stock reporting | Analyst | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Profitability | 2 Recurring Cycle | SKU & product profitability analysis | Analyst / ATL | 3 hrs/month
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Channel | 2 Recurring Cycle | Sales & channel performance reporting | Analyst / ATL | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Costing | 2 Recurring Cycle | COGS & landed cost analysis | Analyst / ATL | 2 hrs/month
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Cash Flow | 2 Recurring Cycle | Cash-flow & inventory planning | Analyst / ATL | 3 hrs/month
|  | Cin7 Core Monthly Constroller Support - Reporting & Analysis | Advisory | 2 Recurring Cycle | Advisory & review call | Consultant PM | 2 hrs/month

## 1 Cin7 Core Setup
1 Cin7 Core Setup — Implementation Plan
Template based on the Advanced package (6-8 week, high-complexity build). Starter/Growth engagements use a subset of these phases — drop manufacturing/3PL/multi-warehouse tasks for Starter, drop full manufacturing for Growth.
Task ID | Phase | Workstream | Task | VNC Owner | Predecessor
T01 | 1 Master Data | PM | Kickoff & project charter agreed | Onboarding Consultant
T02 | 1 Master Data | Design | Confirm in-scope entities (SKUs, locations, channels, suppliers, customers) | Onboarding Consultant | T01
T03 | 1 Master Data | Design | Costing method sign-off (average cost — irreversible) | Client Controller | T01
T04 | 1 Master Data | Design | COA & Cin7→Xero/QBO GL mapping design | Technical Consultant | T02
T05 | 1 Master Data | Design | Product & location hierarchy definition | Onboarding Consultant | T02
T06 | 1 Master Data | Migration | Extract existing product masters | Client PM | T01
T07 | 1 Master Data | Migration | Cleanse & map to Cin7 import templates | Analyst | T06
T08 | 1 Master Data | Migration | Reconcile pre-cutover additions | Client PM | T06
T09 | 1 Master Data | Migration | Mock load #1 + validation | Onboarding Consultant | T07
T10 | 1 Master Data | Migration | Import finished SKUs | Analyst | T09
T11 | 1 Master Data | Migration | Import BOMs (manufacturers) | Analyst | T10
T12 | 1 Master Data | Migration | Import supplier & customer records | Analyst | T09
T13 | 1 Master Data | Migration | Configure opening stock balances as of cutover date | Onboarding Consultant | T10
T14 | 1 Master Data | Migration | Mock load #2 + full validation | Onboarding Consultant | T13
T15 | 2 Config | Config | Configure environment (assembly/BOM if applicable) | Technical Consultant | T05
T16 | 2 Config | Config | Set up stock management module | Onboarding Consultant | T15
T17 | 2 Config | Config | Set up sales module & document templates | Onboarding Consultant | T15
T18 | 2 Config | Config | Set up purchasing module | Onboarding Consultant | T15
T19 | 2 Config | Config | Map PO/SO/inventory movement/COGS workflows | Technical Consultant | T16
T20 | 2 Config | Config | Configure costing method column | Technical Consultant | T03
T21 | 2 Config | Config | Set up landed costs & supplier expense allocation | Technical Consultant | T19
T22 | 2 Config | Integration | Configure Cin7↔Xero/QBO sync (valuation, COGS) | Technical Consultant | T04
T23 | 2 Config | Integration | Validate sync in test environment | Technical Consultant | T22
T24 | 3 Testing | Testing | Author UAT scripts (O2C, P2P, IM, F&A) | Onboarding Consultant | T19
T25 | 3 Testing | Testing | Parallel run commences | Client team | T14
T26 | 3 Testing | Testing | UAT execution across cycles | Client Operations Lead | T24
T27 | 3 Testing | Testing | Validate inventory valuation → accounting balance sheet | Client Controller | T23
T28 | 3 Testing | Testing | Confirm Cin7↔accounting parity (opening, COGS, recon) | Client Controller | T27
T29 | 3 Testing | Testing | Resolve data discrepancies | Technical Consultant | T26
T30 | 3 Testing | Testing | UAT sign-off | Client Project Sponsor | T26
T31 | 4 Go-Live | Training | Prepare training materials & quick-reference cards | Onboarding Consultant | T19
T32 | 4 Go-Live | Training | Role-based user training sessions | Onboarding Consultant | T31
T33 | 4 Go-Live | Cutover | Prepare cutover runbook | Onboarding Consultant | T28
T34 | 4 Go-Live | Cutover | Go-live readiness sign-off | Client Project Sponsor | T30
T35 | 4 Go-Live | Cutover | Cutover / go-live | Onboarding Consultant | T34
T36 | 4 Go-Live | Hypercare | Weekly post-go-live health checks | Delivery Lead | T35
T37 | 4 Go-Live | Reporting | Build reporting templates (sales, ops, purchasing) | Consultant | T35
T38 | 4 Go-Live | Reporting | Configure month-of-stock availability reporting | Consultant | T35
T39 | 4 Go-Live | F&A | First month-end close with client | Client Controller | T35
T40 | 4 Go-Live | Reporting | Deliver monthly controller reports (margin, BOM cost, COGS, trends) | Delivery Lead | T39
T41 | 4 Go-Live | PM | Hypercare complete & closeout; handoff to ongoing support | Onboarding Consultant | T36
1 Cin7 Core Setup — Milestone Tracker
Milestone ID | Milestone | Target Timing | Owner | Status | Evidence / Acceptance
M01 | Kickoff complete; charter agreed | Week 1 | Onboarding Consultant | Not Started | Signed charter
M02 | Master data extracted & cleansed | Week 1 | Client PM | Not Started | Migration workbook v1
M03 | Design sign-off (costing, GL mapping, hierarchy) | Week 1 | Client Controller | Not Started | Signed design note
M04 | Data import + opening stock loaded | Week 2 | Onboarding Consultant | Not Started | Reconciled counts & values
M05 | Core configuration complete | Week 3 | Technical Consultant | Not Started | Build log
M06 | Accounting integration live in test | Week 4 | Technical Consultant | Not Started | Sync validation
M07 | Parallel run commences | Week 4 | Client PM | Not Started | Parallel log opened
M08 | UAT sign-off (O2C, P2P, IM, F&A) | Week 4 | Client Operations Lead | Not Started | Signed UAT scripts
M09 | Cin7↔Accounting parity confirmed | Week 4 | Client Controller | Not Started | Reconciliation pack
M10 | Training complete & go-live readiness sign-off | Week 5 | Client Project Sponsor | Not Started | Readiness checklist
M11 | Go-live / cutover | Week 5 | Onboarding Consultant | Not Started | Smoke-test results
M12 | First month-end close + reporting templates delivered | Week 6 | Client Controller | Not Started | Close pack
M13 | Hypercare complete; handoff to ongoing support | Week 6 | Onboarding Consultant | Not Started | Closeout report

## 2 Rescue & Clean-Up
2 Rescue & Clean-Up — Implementation Plan
Template sized for a 6-week engagement (mid-point of the $999-8,999 / 2-8 week range). For shorter/smaller engagements, compress phases 2-3 and 4-5 in parallel rather than dropping tasks.
Task ID | Phase | Workstream | Task | VNC Owner | Predecessor
T01 | 1 Diagnosis | PM | Kickoff call & scope confirmation | Onboarding Consultant
T02 | 1 Diagnosis | Access | Collect system access (Cin7, Xero/QBO, Shopify/Amazon, A2X) | Onboarding Consultant | T01
T03 | 1 Diagnosis | Audit | Inventory accuracy & valuation audit | Technical Consultant | T02
T04 | 1 Diagnosis | Audit | Accounting integration health audit (sync, mapping, postings) | Technical Consultant | T02
T05 | 1 Diagnosis | Audit | Sales channel connections audit (payout recon health) | Technical Consultant | T02
T06 | 1 Diagnosis | Audit | Workflow gaps & manual workaround audit | Onboarding Consultant | T02
T07 | 1 Diagnosis | Audit | Stock movement & COGS accuracy audit | Technical Consultant | T02
T08 | 1 Diagnosis | Audit | Reporting reliability & data trust audit | Onboarding Consultant | T02
T09 | 1 Diagnosis | Findings | Findings documented & priority-ranked (Red/Amber/Green) | Practice Lead | T03,T04,T05,T06,T07,T08
T10 | 2 Reconciliation | Recon | Reconcile stock quantities across locations | Analyst | T09
T11 | 2 Reconciliation | Recon | Reconcile valuations & landed costs | Consultant | T09
T12 | 2 Reconciliation | Recon | Reconcile warehouse balances | Analyst | T09
T13 | 2 Reconciliation | Recon | Bank/control account reconciliation baseline | Consultant | T09
T14 | 3 Error Correction | Fix | Fix SKU mapping issues | Technical Consultant | T10
T15 | 3 Error Correction | Fix | Remove duplicate records | Analyst | T10
T16 | 3 Error Correction | Fix | Correct incorrect postings | Technical Consultant | T13
T17 | 3 Error Correction | Fix | Repair broken integrations | Technical Consultant | T04
T18 | 4 Standardisation | Standardise | Align SKU / category / location structure | Delivery Lead | T14,T15
T19 | 4 Standardisation | Standardise | Standardise workflows across systems | Delivery Lead | T18
T20 | 4 Standardisation | Document | Document standardised SOPs | Onboarding Consultant | T19
T21 | 5 Integration Stabilisation | Stabilise | Stabilise accounting system integration | Technical Consultant | T17
T22 | 5 Integration Stabilisation | Stabilise | Stabilise e-commerce channel & A2X integration | Technical Consultant | T17
T23 | 5 Integration Stabilisation | Stabilise | Stabilise shipping tool integrations | Technical Consultant | T17
T24 | 5 Integration Stabilisation | Validate | Validate stability across 2 consecutive sync cycles | Technical Consultant | T21,T22,T23
T25 | 6 Handover | Sign-off | Historical data clean-up sign-off | Practice Lead | T24
T26 | 6 Handover | Handover | Prepare handover pack (findings, fixes, SOPs) | Onboarding Consultant | T25
T27 | 6 Handover | Handover | Handover call to recurring delivery team | Delivery Lead | T26
T28 | 6 Handover | Transition | Transition to Monthly Support confirmed | Practice Lead | T27
2 Rescue & Clean-Up — Milestone Tracker
Milestone ID | Milestone | Target Timing | Owner | Status | Evidence / Acceptance
M01 | Kickoff & access collected | Week 1 | Onboarding Consultant | Not Started | Access log signed off
M02 | Diagnosis complete, priority list delivered | Week 1-2 | Practice Lead | Not Started | Written findings, Red/Amber/Green list
M03 | Reconciliation baseline set | Week 2-3 | Consultant | Not Started | Reconciled stock/valuation pack
M04 | Errors corrected & signed off | Week 3-4 | Technical Consultant | Not Started | Error log with resolutions
M05 | Systems standardised | Week 4-5 | Delivery Lead | Not Started | Standardisation SOP doc
M06 | Integrations stabilised & validated | Week 5-6 | Technical Consultant | Not Started | 2-cycle stability report
M07 | Clean handover to ongoing support complete | Week 6 | Practice Lead | Not Started | Signed handover pack

## 3 System Assessment
3 System Assessment — Implementation Plan
Fixed 1-2 week engagement (USD 999-2,499). Timing shown in days, not weeks, given the compressed duration. Maps directly to the brochure's 'What We Audit' and 'What You Walk Away With' sections.
Task ID | Phase | Workstream | Task | VNC Owner | Predecessor
T01 | 1 Kickoff | PM | Kickoff call (45-60 min): business model, warehouses/3PL, channels, pain points | Onboarding Consultant
T02 | 1 Kickoff | Scope | Confirm systems in use (Cin7, Xero/QBO/MYOB, Shopify/Amazon, A2X, shipping) | Onboarding Consultant | T01
T03 | 1 Kickoff | Scope | Confirm assessment boundaries & expected deliverables | Practice Lead | T01
T04 | 2 Access & Data | Collection | Collect read-only system access | Onboarding Consultant | T02
T05 | 2 Access & Data | Collection | Request key reports (valuation, stock on hand, open SO/PO, payouts, TB) | Onboarding Consultant | T04
T06 | 2 Access & Data | Tracking | Maintain missing-items list | Onboarding Consultant | T05
T07 | 3 System Health Check | Audit | Inventory accuracy & valuation review | Technical Consultant | T04
T08 | 3 System Health Check | Audit | Accounting integration health review | Technical Consultant | T04
T09 | 3 System Health Check | Audit | Sales channel connections review | Technical Consultant | T04
T10 | 3 System Health Check | Audit | Stock movement & COGS accuracy review | Technical Consultant | T04
T11 | 3 System Health Check | Audit | Workflow gaps & manual workaround review | Onboarding Consultant | T04
T12 | 3 System Health Check | Audit | Reporting reliability & data trust review | Onboarding Consultant | T04
T13 | 4 Gap Analysis | Analysis | Process gap analysis | Onboarding Consultant | T07,T08,T09,T10,T11,T12
T14 | 4 Gap Analysis | Analysis | Data gap analysis (mappings, duplicates, categorisation) | Technical Consultant | T13
T15 | 4 Gap Analysis | Analysis | Control gap analysis | Onboarding Consultant | T13
T16 | 4 Gap Analysis | Testing | Practical data-quality tests (stock vs valuation trend, top-SKU cost checks) | Analyst | T14
T17 | 5 Workflow Review | Mapping | Map procure-to-pay end-to-end | Onboarding Consultant | T13
T18 | 5 Workflow Review | Mapping | Map order-to-cash end-to-end | Onboarding Consultant | T13
T19 | 5 Workflow Review | Mapping | Map inventory movements & identify break points | Onboarding Consultant | T17,T18
T20 | 6 Roadmap & Handover | Roadmap | Build prioritised roadmap (P1/P2/P3, effort bands, dependencies) | Practice Lead | T16,T19
T21 | 6 Roadmap & Handover | Report | Prepare written assessment (plain language, no jargon) | Onboarding Consultant | T20
T22 | 6 Roadmap & Handover | Handover | Handover call (45-60 min) | Practice Lead | T21
T23 | 6 Roadmap & Handover | Recommendation | Recommend next path: A) Clean Implementation or B) Rescue + Implementation | Practice Lead | T22
3 System Assessment — Milestone Tracker
Milestone ID | Milestone | Target Timing | Owner | Status | Evidence / Acceptance
M01 | Kickoff complete | Day 1 | Onboarding Consultant | Not Started | Scope confirmation notes
M02 | Access & data collected | Day 2-3 | Onboarding Consultant | Not Started | Access log, reports received
M03 | System health check complete (6 audit areas) | Day 4-6 | Technical Consultant | Not Started | Audit findings by area
M04 | Gap analysis & workflow mapping complete | Day 7-9 | Onboarding Consultant | Not Started | Gap list + workflow maps
M05 | Roadmap built | Day 10-11 | Practice Lead | Not Started | P1/P2/P3 roadmap doc
M06 | Handover call complete, path recommended | Day 12-14 | Practice Lead | Not Started | Written assessment + recommendation

## 4 Inventory Accounting
4 Inventory Accounting — Implementation Plan
This is a recurring service, not a one-time build — Phase 1 is a one-time onboarding; Phase 2 repeats every month for the life of the engagement. Milestone M04 recurs monthly rather than closing out once.
Task ID | Phase | Workstream | Task | VNC Owner | Predecessor
T01 | 1 Onboarding | Scope | Confirm signed scope & planned monthly hours | Delivery Lead
T02 | 1 Onboarding | Validation | Validate SOP baseline (from Setup/Assessment/Rescue handover) | Delivery Lead | T01
T03 | 1 Onboarding | Rhythm | Define recurring rhythm (weekly + monthly checks) | Delivery Lead | T02
T04 | 1 Onboarding | Staffing | Assign Consultant/Analyst to account | Delivery Lead | T01
T05 | 1 Onboarding | Trial | First cycle trial run & internal review | Delivery Lead | T03,T04
T06 | 2 Recurring Monthly Cycle | P2P | Procure-to-pay processing (purchases, receipts, bills) | Analyst | T05
T07 | 2 Recurring Monthly Cycle | O2C | Order-to-cash processing (orders, invoices, fulfilment) | Analyst | T05
T08 | 2 Recurring Monthly Cycle | Integration | Cin7 ↔ Accounting integration check | Consultant | T05
T09 | 2 Recurring Monthly Cycle | Recon | Stock reconciliation (Cin7 vs accounting), monthly | Consultant | T08
T10 | 2 Recurring Monthly Cycle | Costing | Landed cost & COGS accuracy check | Consultant | T09
T11 | 2 Recurring Monthly Cycle | Reporting | SKU-level profitability prep | Consultant | T09
T12 | 2 Recurring Monthly Cycle | Controls | Inventory controls & variance review | Analyst | T09
T13 | 2 Recurring Monthly Cycle | Controls | Stock adjustment monitoring | Analyst | T12
T14 | 2 Recurring Monthly Cycle | Review | Monthly inventory & operational review pack | Delivery Lead | T06,T07,T10,T11,T13
4 Inventory Accounting — Milestone Tracker
Milestone ID | Milestone | Target Timing | Owner | Status | Evidence / Acceptance
M01 | Onboarding handover accepted | Week 1 | Delivery Lead | Not Started | Signed scope + SOP baseline
M02 | First monthly cycle completed & reviewed | Month 1 | Delivery Lead | Not Started | First monthly review pack
M03 | Recurring rhythm stabilised (3 consecutive clean cycles) | Month 3 | Delivery Lead | Not Started | 3 months' review packs, no material variance
M04 (recurring) | Monthly review pack delivered | Every month, by day 10 | Delivery Lead | Not Started | Monthly inventory & ops review pack

## 5 E-Commerce Accounting
5 E-Commerce Accounting — Implementation Plan
Recurring service. Phase 1 is one-time onboarding; Phase 2 repeats monthly. Often runs in parallel with Inventory Accounting for the same client rather than as a standalone engagement.
Task ID | Phase | Workstream | Task | VNC Owner | Predecessor
T01 | 1 Onboarding | Connect | Connect sales channels (Shopify/Amazon/WooCommerce/etc.) | Technical Consultant
T02 | 1 Onboarding | Configure | Configure A2X / Dext Commerce | Technical Consultant | T01
T03 | 1 Onboarding | Validate | Validate fee/refund/chargeback logic | Technical Consultant | T02
T04 | 1 Onboarding | Rhythm | Define payout reconciliation rhythm | Delivery Lead | T02
T05 | 1 Onboarding | Trial | First payout reconciliation trial run | Consultant | T03,T04
T06 | 2 Recurring Monthly Cycle | Revenue | Multi-channel revenue recognition | Analyst | T05
T07 | 2 Recurring Monthly Cycle | Recon | Payout reconciliation (Shopify/Amazon/gateways) | Consultant | T05
T08 | 2 Recurring Monthly Cycle | Match | Three-way match (channel → Cin7 → accounting) | Consultant | T06,T07
T09 | 2 Recurring Monthly Cycle | Costing | Stock, COGS & margin alignment | Consultant | T08
T10 | 2 Recurring Monthly Cycle | Fees | Fee & refund management | Analyst | T07
T11 | 2 Recurring Monthly Cycle | Reporting | Omni-channel reporting | Delivery Lead | T08,T09,T10
T12 | 2 Recurring Monthly Cycle | Health | Automation/integration health check (as needed) | Technical Consultant | T11
5 E-Commerce Accounting — Milestone Tracker
Milestone ID | Milestone | Target Timing | Owner | Status | Evidence / Acceptance
M01 | Channel connections & A2X/Dext live | Week 1-2 | Technical Consultant | Not Started | Integration test log
M02 | First payout reconciliation complete | Month 1 | Consultant | Not Started | First reconciliation pack
M03 | Recurring rhythm stabilised | Month 2-3 | Delivery Lead | Not Started | 2 consecutive clean monthly packs
M04 (recurring) | Monthly omni-channel report delivered | Every month | Delivery Lead | Not Started | Omni-channel report pack

## 6 Reporting & Analysis
6 Reporting & Analysis — Implementation Plan
Recurring service, tiered (Visibility Essentials 6 reports / Operational Insight 10 reports / Decision Intelligence 15 reports + written analysis). Cadence and report count scale with the client's selected tier.
Task ID | Phase | Workstream | Task | VNC Owner | Predecessor
T01 | 1 Onboarding | Scope | Confirm reporting tier (Visibility Essentials / Operational Insight / Decision Intelligence) | Practice Lead
T02 | 1 Onboarding | Scope | Define report set & delivery frequency | Practice Lead | T01
T03 | 1 Onboarding | Build | Build initial dashboard/report templates | Consultant | T02
T04 | 1 Onboarding | Rhythm | Agree review call cadence | Practice Lead | T02
T05 | 2 Recurring Cycle | Inventory | Inventory & stock reporting | Analyst | T03
T06 | 2 Recurring Cycle | Profitability | SKU & product profitability analysis | Consultant | T05
T07 | 2 Recurring Cycle | Channel | Sales & channel performance reporting | Consultant | T05
T08 | 2 Recurring Cycle | Costing | COGS & landed cost analysis | Consultant | T05
T09 | 2 Recurring Cycle | Cash Flow | Cash-flow & inventory planning | Consultant | T05
T10 | 2 Recurring Cycle | Advisory | Advisory & review call | Practice Lead | T06,T07,T08,T09
6 Reporting & Analysis — Milestone Tracker
Milestone ID | Milestone | Target Timing | Owner | Status | Evidence / Acceptance
M01 | Tier confirmed & templates built | Week 1-2 | Practice Lead | Not Started | Signed tier selection + template set
M02 | First report pack delivered | Month 1 | Consultant | Not Started | First tier-appropriate report pack
M03 | Review cadence stabilised | Month 2 | Practice Lead | Not Started | 2 consecutive review calls held
M04 (recurring) | Report pack + review call delivered | Per tier cadence (monthly/quarterly) | Practice Lead | Not Started | Report pack + call notes